## Sheet1
PROJECT NAME :- GET ESCAPING
Project Budget: Estimated: $0.00 ¦ Baseline: $0.00 ¦ Task Costs: Estimated: $0.00 ¦ Baseline: $0.00 ¦ Actual: $0.00
WBS | Task | Priority | Status | Resource | Start | Finish | Duration | Work | Done | % Complete |  | W3 |  |  | W4 |  |  | W5 |  |  | W6 |  |  | W7 |  |  | W8 |  |  | W9 |  |  | W10 |  |  | W11 |  |  | W12 |  |  | W13 |  |  | W14 |  |  | W15 |  |  | W16
[11 empty] | 17 | 21 | 22 | 24 | 28 | 29 | 31 | 4 | 5 | 7 | 11 | 12 | 14 | 18 | 19 | 21 | 25 | 26 | 28 | 4 | 5 | 7 | 11 | 12 | 14 | 18 | 19 | 21 | 25 | 26 | 28 | 1 | 2 | 4 | 8 | 9 | 11 | 15 | 16 | 18 | 22 | 23
[11 empty] | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S | M | F | S
1 | Topic Confirmation | HIGH |  |  | Week 3 | Week 3 | 1 Day |  | 1 | 4%
2 | Learning Web Development languages(HTML , CSS , JS) | HIGH | Planned | YT | Week 3 | Week 4 | 12 Days |  | 1 | 10%
3 | Making Gantt Chart | MODERATE |  |  | Week 5 | Week 5 | 1 Day |  | 1 | 15%
4 | Learning Project Management Tools | MODERATE |  |  | Week 5 | Week 5 | 1 Day |  | 1 | 20%
5 | Creating Home Screen | HIGH |  |  | Week 5 | Week 5 | 1 Day |  | 1 | 25%
6 | Assigining Different Modules to Team Memebers | MODERATE |  |  | Week 5 | Week 6 | 2 Days |  | 1 | 28%
7 | Header Section | HIGH |  |  | Week 6 | Week 6 | 4 Days |  | 1 | 35%
8 | Footer Section | HIGH |  |  | Week 6 | Week 6 | 3 Days |  | 1 | 40%
9 | Home Section | HIGH |  |  | Week 6 | Week 7 | 8 Days |  | 1 | 45%
10 | Book Section | HIGH |  |  | Week 8 | Week 8 | 6 Days |  | 1 | 49%
11 | Packages Section | HIGH |  |  | Week 9 | Week 9 | 6 Days |  | 1 | 54%
12 | Service Section | HIGH |  |  | Week 9 | Week 10 | 7 Days |  | 1 | 59%
13 | Gallery Section | HIGH |  |  | Week 10 | Week 10 | 6 Days |  | 1 | 64%
14 | Review Section | HIGH |  |  | Week 11 | Week 11 | 6 Days |  | 1 | 68%
15 | Contact Section | HIGH |  |  | Week 12 | Week 12 | 6 Days |  | 1 | 73%
16 | Brand Slider | HIGH |  |  | Week 12 | Week 13 | 6 Days |  | 1 | 79%
17 | Learning backend(Node JS , MongoDB) | HIGH |  | YT | Week 13 | Week 14 | 6 Days |  | 1 | 82%
18 | Register Page | HIGH |  |  | Week 14 | Week 15 | 2 Days |  | 1 | 86%
19 | Login Page | HIGH |  |  | Week 14 | Week 15 | 2 Days |  | 1 | 91%
20 | Plan Section | HIGH |  |  | Week 14 | Week 15 | 2 Dyas |  | 1 | 95%
21 | Designing database | MODERATE |  |  | Week 15 | Week 16 | 4 Days |  | 1 | 97%
22 | Project report | MODERATE |  |  | Week 16 | Week 16 | 2 Days |  | 1 | 98%
23 | Project PPt | MODERATE |  |  | Week 16 | Week 16 | 2 Days |  | 1 | 99%
24 | Preperation | HIGH |  |  | Week 16 | Week 16 | 4 Days |  | 1 | 100%